## Sheet1
Date | Milestone | Description
2014-07-07 | The project starts | Estimated date
2014-07-14 | The pages should be set online | To test whether Microsoft Azure is available for the project
| The testing back-end apis on Azure should be run through | To test whether Microsoft Azure is available for the project
2014-07-20 | The user authentication should be implemented | To set the system into a security environment
| The Login and Index page should be done | User will be able to login the system
2014-07-27 | The Project page should be done | User will be able to create and view a project
2014-08-03 | The Task and User page should be done | User will be able to create users. User will be able to create tasks and assign users to tasks
2014-08-10 | The Config page should be done | User will be able to configurate the settings
2014-08-17 | The Manage page should be done | User will be able to manage and delete all the objects in the system
| The arts materials such as icons should be done | Icons specifically customized for the system will be set
2014-08-24 | The Workload component of Visualization page should be done | An interface that demonstrates the workloads of users